## Matrix
|  |  |  | Engineering Drawings Status ZED East Project | [6 empty] | Data Date |  | 2026-07-26
Structural | [16 empty] | MEP
Parking | Formwork |  |  |  |  | Rebar | [8 empty] | Post Tension |  | Parking | Mechanical |  |  |  |  | Electrical
Area/Item | Columns | PC | RC | Slab | Slab On Grades | Isolated footing | Strip Footing | Ground Beam | Rebar Of sumpits | Columns | Retaining Walls | Slab | Beam | Slab On Grades | P.T Design | P.T Shop drawing | Area/Item | HVAC | Water Supply | Drainage High-Level | Drainage Low-Level | Firefighting | Lighting System | Power System | Power HVAC System | Cable Routing System | Panel Board Schedule | MCC System | Earthing System | Fire Alarm System | ECSD System | Structure Cabling System | CCTV System | Access Control System | Service Provider System
Z1,P1(W) | Approved | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Approved | Approved | Approved | Approved | Approved | Not Submitted | Approved | Approved | Z1,All Parts | Not Submitted | Not Submitted | Resubmit | Resubmit | Not Submitted | Approved | Approved | Approved | Resubmit | Not Submitted | Not Submitted | Not Submitted | Not Submitted | Resubmit | Approved | Not Submitted | Not Submitted | Under Review
Z1,P2(N) | Approved | Approved | Approved | Approved | Under Review | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Approved | Not Submitted | Under Review | Approved | Z2,All Parts | Not Submitted | Not Submitted | Not Submitted | Resubmit | Not Submitted | Approved | Approved | Approved | Not Submitted | Not Submitted | Not Submitted | Not Submitted | Not Submitted | Not Submitted | Approved | Not Submitted | Not Submitted | Not Submitted
Z1,P3(L) | Approved | Approved | Approved | Approved | Under Review | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Approved | Not Submitted | Under Review | Approved | Z3,All Parts | Not Submitted | Not Submitted | Resubmit | Resubmit | Not Submitted | Approved | Approved | Approved | Not Submitted | Not Submitted | Not Submitted | Not Submitted | Not Submitted | Not Submitted | Approved | Not Submitted | Not Submitted | Not Submitted
Z1,P4( C) | Approved | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Approved | Not Submitted | Approved | Approved | No. of Submissions | 0 | 0 | 2 | 3 | 0 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 1
Z1,P5( E) | Approved | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Approved | Approved | Approved | Approved | Approved | Not Submitted | Under Review | Approved | Remaining | 3 | 3 | 1 | 0 | 3 | 0 | 0 | 0 | 2 | 3 | 3 | 3 | 3 | 2 | 0 | 3 | 3 | 2
Z1,P6(X) | Approved | Approved | Approved | Under Review | Approved | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Approved | Not Submitted | Under Review | Not Submitted
Z1,P7(G) | Approved | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Approved | Approved | Approved | Under Review | Under Review | Not Submitted | Under Review | Not Submitted
Z1,P8(Y) | Approved | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Approved | Not Submitted | Under Review | Approved
Z1,P9(M) | Approved | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Not Submitted | Approved | Approved | Under Review | Approved | Not Submitted | Under Review | Resubmit
Z1,P10(EE) | Approved | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Approved | Approved | Approved | Approved | Approved | Not Submitted | Under Review | Approved
Z2,P1(H) | Approved | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Approved | Not Submitted | Under Review | Approved
Z2,P2(V) | Approved | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Approved | Not Submitted | Under Review | Approved
Z2,P3(I) | Approved | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Approved | Not Submitted | Under Review | Approved
Z2,P4(T) | Approved | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Under Review | Approved | Approved | Approved | Approved | Not Submitted | Under Review | Approved
Z2,P5(U) | Approved | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Not Submitted | Approved | Approved | Not Submitted | Not Submitted | Not Submitted | Under Review | Not Submitted
Z2,P6(F) | Approved | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Approved | Approved | Approved | Under Review | Not Submitted | Not Submitted | Under Review | Not Submitted
Z2,P7(O) | Approved | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Approved | Not Submitted | Under Review | Resubmit
Z2,P8(BB) | Approved | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Approved | Not Submitted | Under Review | Approved
Z2,P9(CC) | Approved | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Approved | Not Submitted | Under Review | Approved
Z2,P10(B) | Approved | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Approved | Approved | Approved | Approved | Approved | Not Submitted | Under Review | Resubmit
Z3,P1(A) | Approved | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Approved | Not Submitted | Under Review | Approved
Z3,P2(DD) | Approved | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Approved | Not Submitted | Under Review | Under Review
Z3,P3(P) | Approved | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Not Submitted | Approved | Approved | Under Review | Approved | Not Submitted | Under Review | Not Submitted
Z3,P4(K) | Approved | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Approved | Not Submitted | Under Review | Under Review
Z3,P5(D) | Approved | Approved | Approved | Under Review | Not Submitted | Approved | Approved | Approved | Approved | Approved | Approved | Not Submitted | Not Submitted | Not Submitted | Not Submitted | Not Submitted
Z3,P6(S) | Approved | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Approved | Not Submitted | Under Review | Resubmit
Z3,P7(Q) | Approved | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Resubmit | Approved | Approved | Approved | Approved | Not Submitted | Under Review | Under Review
Z3,P8( R) | Approved | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Approved | Not Submitted | Under Review | Approved
Z3,P9(AA) | Approved | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Approved | Approved | Approved | Approved | Approved | Not Submitted | Under Review | Approved
Z3,P10(Z) | Approved | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Approved | Not Submitted | Under Review | Under Review
Z3,P11(J) | Approved | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Not Submitted | Approved | Approved | Approved | Approved | Not Submitted | Approved | Approved
No. of Submissions | 31 | 31 | 31 | 31 | 3 | 31 | 31 | 31 | 10 | 31 | 31 | 29 | 28 | 0 | 30 | 25
Remaining | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 21 | 0 | 0 | 2 | 3 | 31 | 1 | 6